## Amazon Canada Gantt V2
Tasks | Assigned To | Duration | Start Date | End Date | Predecessors | Health | Status | Notes | % Complete
External Fixed Milestones |  | 33d | 2026-09-18 | 2026-11-05
Prime Day Shipment Cutoff |  | 0 | 2026-09-18 | 2026-09-18
BFCM Shipment Cutoff |  | 0 | 2026-11-05 | 2026-11-05
PHASE 1 - Define & Qualify |  | 16d | 2026-07-10 | 2026-07-31
NPN license compilation (4 launch SKUs) | Allison | 11d | 2026-07-10 | 2026-07-24 |  |  | Complete
Assess all 4 launch SKUs vs. 90-120% spec | Shilpa | 1d | 2026-07-17 | 2026-07-17
Send current packaging files to Allison | Alicia | 1d | 2026-07-27 | 2026-07-27
Gowling NPN placement confirmation | JP Powers | 5d | 2026-07-27 | 2026-07-31 | 5
Submit English label text to Gowling | Allison | 1d | 2026-07-28 | 2026-07-28 | 5, 7
French translations returned from Gowling | Mary Catherine | 3d | 2026-07-29 | 2026-07-31 | 9
Determine quantity required for Canada launch | Amrata / Arlene | 5d | 2026-07-27 | 2026-07-31
Entity address update completed | Arlene / Brock | 6d | 2026-07-24 | 2026-07-31
Logistics call with Sara | Siddhi / Arlene / Justin / Kate | 1d | 2026-07-30 | 2026-07-30
GATE 1 - Design & Sourcing Inputs Locked | Siddhi | 0 | 2026-07-31 | 2026-07-31 | 8, 10, 11, 12, 13
PHASE 2 - Design, Approval & Sourcing |  | 35d | 2026-07-24 | 2026-09-11
2A . Forecast & PO Release |  | 5d | 2026-08-03 | 2026-08-07
S&OP update / Canada forecast build | Amrata / Arlene | 3d | 2026-08-03 | 2026-08-05 | 11
Forecast agreed & signed off | Kim / Justin / Kate | 1d | 2026-08-06 | 2026-08-06 | 17
POs placed with co-manufacturers | Kate | 1d | 2026-08-07 | 2026-08-07 | 18
2B . Creative & Packaging |  | 29d | 2026-08-03 | 2026-09-11 |  |  | Complete
Allison delivers complete ClickUp brief to creative | Allison | 1d | 2026-08-03 | 2026-08-03 | 14
Creative kickoff with Michelle | Alicia / Michelle | 1d | 2026-08-04 | 2026-08-04 | 21
Bilingual artwork design (4 SKUs) | Michelle | 15d | 2026-08-05 | 2026-08-25 | 22
Artwork submitted to Allison for Gowling review | Alicia | 1d | 2026-08-26 | 2026-08-26 | 23
Gowling artwork review + revisions | JP Powers | 10d | 2026-08-27 | 2026-09-10 | 24
Artwork approved by Gowling | JP Powers | 1d | 2026-09-11 | 2026-09-11 | 25
2C . Carton Sourcing |  | 11d | 2026-08-03 | 2026-08-17
Carton MOQ + print quote confirmation | Kate | 6d | 2026-08-03 | 2026-08-10 | 11
Repack sequencing plan (vs. Walmart / Target) | Kate | 11d | 2026-08-03 | 2026-08-17
2D . Amazon Account & Platform |  | 27d | 2026-07-24 | 2026-08-31
Bank information verification resolved | Arlene | 11d | 2026-07-24 | 2026-08-07
Transparency Program / UPC=ASIN confirmation | Arlene | 11d | 2026-07-31 | 2026-08-14
Seller account reactivated | Arlene / Kat | 10d | 2026-08-10 | 2026-08-21 | 12, 31
Confirm ASINs | Arlene / Brock | 6d | 2026-08-24 | 2026-08-31 | 33
HC documentation package for Amazon | Allison | 5d | 2026-08-03 | 2026-08-07 | 5, 8
2E . Logistics & Fulfillment Route |  | 16d | 2026-07-31 | 2026-08-21
Evaluate Forceget + Frisbi (3PL options) | Justin / Kate | 5d | 2026-07-31 | 2026-08-06 | 13
Confirm customs broker (direct-to-FC capable) | Justin | 10d | 2026-07-31 | 2026-08-13 | 13
Fulfillment route decision finalized | Justin / Kate | 1d | 2026-08-14 | 2026-08-14 | 37, 38
Contract Canada 3PL / return facility | Justin | 5d | 2026-08-17 | 2026-08-21 | 39
GATE 2 - Production Committed | Kate / Siddhi | 0 | 2026-09-11 | 2026-09-11 | 19, 26, 28, 34, 40, 35
PHASE 3 - Produce & Release |  | 70d | 2026-08-10 | 2026-11-18
3A . Packet Production & Testing |  | 70d | 2026-08-10 | 2026-11-18
Packet production & delivery (12 wks) | Kate / INW | 60d | 2026-08-10 | 2026-11-03 | 19
Packets received | Kate | 0 | 2026-11-03 | 2026-11-03 | 44
Aliquot Canada lot & per-lot CoA testing (2 wks) | Shilpa | 10d | 2026-11-04 | 2026-11-18 | 45
3B . Carton Print & Delivery |  | 30d | 2026-09-14 | 2026-10-26
Carton print run & delivery (6 wks) | Kate / Printer | 30d | 2026-09-14 | 2026-10-26 | 26
Bilingual cartons received | Kate | 0 | 2026-10-26 | 2026-10-26 | 48
3C . Amazon Storefront Build |  | 17d | 2026-09-14 | 2026-10-06
Canada bilingual image uploads | Brock | 6d | 2026-09-14 | 2026-09-21 | 41
Listing content review with Kat | Brock / Kat | 11d | 2026-09-22 | 2026-10-06 | 51, 35
Listings built and compliance-approved | Brock | 0 | 2026-10-06 | 2026-10-06 | 34, 52
GATE 3 - Components Received & Released | Kate / Siddhi | 0 | 2026-11-18 | 2026-11-18 | 46, 49, 53
PHASE 4 - Kit, Ship & Launch |  | 27d | 2026-11-19 | 2026-12-30
Kitting / boxing (2 wks) | Justin / Roger | 10d | 2026-11-19 | 2026-12-04 | 54, 29, 32
Shipment preparation | Kate / 3PL | 5d | 2026-12-07 | 2026-12-11 | 56
Cross-border transit & Amazon FC check-in | Kate / 3PL | 10d | 2026-12-14 | 2026-12-28 | 57
Amazon.ca listings go live | Brock / Arlene | 1d | 2026-12-29 | 2026-12-29 | 53, 58
Canada ad campaigns activated | Brock | 1d | 2026-12-30 | 2026-12-30 | 59
GATE 4 - Amazon Canada Launch Live | All | 0 | 2026-12-30 | 2026-12-30 | 60